## Risk Register v2
KHAYA PAYROLL (PTY) LTD — CONSOLIDATED RISK REGISTER v2 (YEAR 1 REVIEW)
Annual review — Month 12 ¦ 256 clients ¦ 54 staff ¦ ~67,000 employee records ¦ Version 2.0
Risk ID | Risk Description | Source | Category | Likelihood (1–3) | Impact (1–3) | Inherent Risk Score | Current Controls | Control Effectiveness | Residual Risk Score | Treatment | Owner | Target Date | Status | Year 1 Change | Notes
R-001 | No Information Officer registered; no Deputy IO; no escalation path. | POPIA | Legal/Regulatory | 1 | 1 | 1 | CEO registered as IO (Month 1). Deputy IO (Head of Customer Success) appointed. Escalation path documented. | High | 1 | Mitigate | CEO / IO | Complete | ✅ Closed | High → Low | Fully remediated. IO/Deputy IO structure tested successfully in Month 7 incident.
R-002 | Over-collection of special personal information (medical/health data); no minimum-necessary standard. | POPIA | Legal/Regulatory | 2 | 2 | 4 | Medical data standard drafted (Month 5) — leave dates and fitness-for-duty status only. Technical enforcement pending (RFC-014). | Medium | 3 | Mitigate | IO / IT Head | Month 14 | 🟡 In Progress | Medium-High → Medium | Standard drafted but not technically enforced. HR admins can still upload full medical certificates.
R-003 | No documented legal basis mapping data categories to POPIA processing conditions. | POPIA | Legal/Regulatory | 1 | 1 | 1 | Legal basis mapping document completed and CEO-approved (Month 3). | High | 1 | Mitigate | IO | Complete | ✅ Closed | Medium-High → Low | Contract necessity confirmed for payroll data; legal obligation confirmed for SARS/tax data.
R-004 | No privacy notice template; clients not supporting employee disclosure obligations. | POPIA | Legal/Regulatory | 1 | 2 | 2 | Privacy notice template v1.0 published (Month 3). Updated post-Month 7 incident (Month 8) to include bulk-email guidance. | High | 1 | Mitigate | IO | Complete | ✅ Closed | Medium-High → Low | Distributed to all 256 clients. Updated after Month 7 incident to include HR admin bulk-email handling guidance.
R-005 | No data retention policy; former employee records persist indefinitely. | POPIA | Operational | 2 | 2 | 4 | Retention policy written and CEO-approved (Month 4). 5-year retention period; 2-week access revocation trigger. Manual review by Deputy IO quarterly. Technical enforcement pending. | Medium | 3 | Mitigate | IO / IT Head | Month 15 | 🟡 In Progress | Medium-High → Medium | Policy written but technical automated flags not yet built. Records managed manually by Deputy IO on quarterly basis.
R-006 | No DPAs with sub-processors (Intercom, SendGrid, Payment Gateway). | POPIA | Legal/Regulatory | 1 | 2 | 2 | DPAs signed with Intercom, SendGrid, Payment Gateway (Month 2). SOC 2 Type II / ISO 27001 evidence received for 3 of 5 vendors. | High | 1 | Mitigate | IO | Mostly complete | 🟡 In Progress | Medium-High → Medium | Original 3 vendors covered. Xero DPA outstanding (onboarded Month 10, DPA under legal review). Gusto DPA signed Month 9.
R-007 | No validation for sensitive data field updates; mispayment risk. | POPIA | Operational | 2 | 2 | 4 | Email confirmation implemented for banking detail updates (Month 5). Quarterly automated data quality scans running since Month 6. | Medium | 3 | Mitigate | IT Head | Month 14 | 🟡 In Progress | Medium-High → Medium | Banking detail confirmation live. ID number confirmation not yet implemented. First scan found 14 records with missing tax numbers — all remediated.
R-008 | No ROPA; employees unaware of data subject rights. | POPIA | Legal/Regulatory | 2 | 2 | 4 | Rights notice published on self-service portal (Month 3). HR workshop conducted for 12 of 256 clients (Month 4). ROPA 60% complete (Month 12). | Medium | 3 | Mitigate | IO | Month 15 | 🟡 In Progress | High → Medium | Rights awareness improved. ROPA in progress — payroll and statutory sections documented; medical/leave section pending Condition 2 technical enforcement.
R-009 | Single-factor auth only; no MFA; no encryption; broad unlogged internal access. | POPIA | Technical | 2 | 3 | 6 | MFA enforced for all 54 staff (Month 4). Access logging live (Month 5). RBAC 60% implemented. ID number encryption confirmed. Banking field encryption in progress. | Medium | 5 | Mitigate | IT Head | Month 14 | 🟡 In Progress | High → Medium | MFA and logging complete. RBAC 40% still on legacy model. Banking field encryption not yet confirmed at rest.
R-010 | No incident response plan; no breach notification procedure. | POPIA | Operational | 1 | 1 | 1 | IRP v1.0 drafted and CEO-approved (Month 2). Successfully activated in Month 7 incident. 72-hour benchmark met (68 hours). Information Regulator acknowledged — no enforcement action. | High | 1 | Mitigate | IO / IT Head | Complete | ✅ Closed | High → Low | IRP tested in live incident. Breach notification issued within 72-hour self-imposed benchmark. No regulatory enforcement action taken.
R-011 | No data subject request process; requests go unmet. | POPIA | Legal/Regulatory | 3 | 3 | 9 | Rights notice published (Month 3). Informal requests handled via support email by Deputy IO. No structured intake form, SLA, or tracking. | Low | 9 | Mitigate | IO / IT Head | Month 14 | 🔴 Open | High → High | Highest priority unresolved POPIA gap at Month 12. Engineering capacity constraints delayed portal form build. Targeted Month 14.
R-012 | No security governance structure; no security policy; no assigned security ownership. | SOC 2 | Operational | 1 | 1 | 1 | IO mandate extended to include security oversight (Month 1). Security policy v1.0 CEO-approved (Month 3). Monthly check-ins established. | High | 1 | Mitigate | CEO / IO | Complete | ✅ Closed | High → Low | 6-month role review now overdue. Growth indicators suggest dedicated Security Lead may be warranted. Formal review scheduled Month 13.
R-013 | No internal reporting channel or external responsible disclosure policy. | SOC 2 | Operational | 1 | 1 | 1 | security@khayapayroll.co.za live (Month 2). Responsible disclosure policy published (Month 2). Anonymous internal channel via HR platform (Month 4). | High | 1 | Mitigate | IO | Complete | ✅ Closed | Medium-High → Low | All channels in place. Security awareness training (1 of 4 sessions) delivered to help staff use them effectively.
R-014 | No formal risk assessment process; risk position unknown. | SOC 2 | Operational | 2 | 2 | 4 | Monthly check-ins running (8 of 10 completed). Quarterly deep-dives (2 of 3 completed). Pre-implementation risk review applied to Gusto and Xero onboarding. | Medium | 3 | Mitigate | IO / IT Head | Ongoing | 🟡 In Progress | Medium-High → Medium | Process established but cadence inconsistent — 2 monthly and 1 quarterly session missed. Q3 review rescheduled to Month 13.
R-015 | No mechanism to verify controls are functioning as intended. | SOC 2 | Operational | 2 | 2 | 4 | Monthly control sign-off checklist running (8 of 10 completed). Weekly access log reviews running. Nessus scans catching vulnerabilities. | Medium | 3 | Mitigate | IO / IT Head | Ongoing | 🟡 In Progress | Medium-High → Medium | Monitoring in place but completion rate mirrors CC3 cadence gap. 2 months of unverified control effectiveness.
R-016 | No formally adopted policies; all recommendations unadopted. | SOC 2 | Operational | 1 | 1 | 1 | Policy template CEO-approved (Month 3). ACP v1.0 approved (Month 3). IRP v1.0 approved (Month 2). Both policies applied in Month 7 incident. | High | 1 | Mitigate | CEO / IO | Mostly complete | ✅ Closed | High → Low | Vendor Management Policy still outstanding (deferred to Month 13). All other priority policies adopted.
R-017 | No device offboarding; departing staff laptops not wiped; no building access controls. | SOC 2 | Technical | 2 | 2 | 4 | Device offboarding procedure drafted (Month 4). Full-disk encryption required for new laptops (Month 5). ID badge access installed at Cape Town office (Month 6). | Medium | 3 | Mitigate | IT Head | Month 15 | 🟡 In Progress | Medium-High → Medium | 7 of 19 remote departures in Year 1 had delayed device return beyond 2-week policy. Enforcement inconsistent for remote staff.
R-018 | No monitoring or detection; no vulnerability scanning; IRP untested. | SOC 2 | Technical | 2 | 2 | 4 | Native login anomaly alerting live (Month 2). Nessus weekly scans running (Month 3) — 3 medium findings remediated. IRP tested Month 7. Tabletop exercise Month 9. | Medium | 3 | Mitigate | IT Head | Ongoing | 🟡 In Progress | High → Medium | No critical vulnerabilities found in Year 1. Native alerting only — SIEM evaluation recommended for Year 2 given growth trajectory.
R-019 | No change management process; code pushed without review or rollback plan. | SOC 2 | Technical | 1 | 1 | 1 | GitLab as authoritative change log (Month 2). RFC template enforced for all changes since Month 3. Revert process documented. 0 production incidents from unreviewed changes in Year 1. | High | 1 | Mitigate | IT Head | Complete | ✅ Closed | High → Low | Strong year — RFC process held under pressure with 3 major feature releases and 1 emergency hotfix (all followed process).
R-020 | No vendor register; no business continuity plan; no client communication plan. | SOC 2 | Operational | 2 | 2 | 4 | Vendor register live (Month 2). Failover system live (Month 6). Client communication plan finalized (Month 5) — tested in Month 7 incident. Manual payroll fallback documented but untested. | Medium | 3 | Mitigate | IO / IT Head | Month 15 | 🟡 In Progress | High → Medium | Month 7 incident tested communication plan successfully (8-hour window met). Manual fallback dry-run not yet scheduled.
R-021 | No SLA; no uptime monitoring; no capacity planning. | SOC 2 | Operational | 1 | 1 | 1 | SLA (99% uptime) in all new contracts since Month 3. UptimeRobot live — 99.2% uptime achieved. Annual capacity review completed Month 11; infrastructure upgrade approved. | High | 1 | Mitigate | IT Head | Complete | ✅ Closed | Medium-High → Low | 2 minor outages (Month 5: 47 min, Month 9: 23 min) — both within SLA allowance. 42% client growth triggered >20% capacity review threshold.
R-022 | [NEW] Rapid staff growth (54%) outpacing security awareness training rollout; new staff largely untrained. | SOC 2 | Operational | 3 | 2 | 6 | 1 of 4 quarterly training sessions delivered (Month 4). Anonymous reporting channel in place but uptake low among new staff. | Low | 6 | Mitigate | IO / Deputy IO | Month 16 | 🔴 Open | New | New risk identified Year 1. ~22 new staff members have not received formal security training. Priority for Year 2 Q1.
R-023 | [NEW] Two new sub-processors (Gusto, Xero) onboarded; Xero DPA outstanding; no SOC 2/ISO evidence for either. | POPIA / SOC 2 | Legal/Regulatory | 2 | 2 | 4 | Gusto DPA signed (Month 9). Xero DPA under legal review (Month 12). Both added to vendor register. SOC 2/ISO 27001 evidence requested. | Low | 4 | Mitigate | IO | Month 13 | 🟡 In Progress | New | New risk identified Year 1. Xero DPA is highest priority — active POPIA s21 gap until resolved.
R-024 | [NEW] Client HR admin bulk-email data handling gap revealed by Month 7 incident. | POPIA | Operational | 2 | 2 | 4 | Privacy notice template updated (Month 8). Bulk-email guidance issued to all clients. New client onboarding checklist updated (Month 9). Not yet verified across all 256 clients. | Medium | 3 | Mitigate | Deputy IO | Month 15 | 🟡 In Progress | New | Partially remediated. New client process updated. Existing 180 clients have not yet completed equivalent training verification.

## Legend
RISK REGISTER v2 — LEGEND & SCORING GUIDE
── INHERENT RISK SCORE ── | Likelihood (1–3) × Impact (1–3) = 1–9
1–2 ● Low | Green — monitor; no urgent action
3–4 ● Low-Medium | Yellow — schedule remediation
5–6 ● Medium-High | Orange — priority remediation required
7–9 ● High | Red — immediate action required
── STATUS KEY ──
✅ Closed | Gap remediated; control in place and functioning
🟡 In Progress | Partially remediated; residual gap remains
🔴 Open | Gap unresolved; original or new finding still applies
[NEW] | Risk identified during Year 1 — not in original assessment
── YEAR 1 CHANGE ── | Shows direction of risk movement from original assessment
High → Low | Significant improvement; control fully implemented
High → Medium | Partial improvement; residual gap remains
Unchanged | No remediation progress in Year 1
New | Risk did not exist at original assessment
── TREATMENT OPTIONS ──
Mitigate | Implement controls to reduce likelihood or impact
Accept | Acknowledge risk; no action (low residual risk)
Transfer | Shift risk to third party (insurance, vendor SLA)
Avoid | Eliminate the activity generating the risk
── SOURCES ──
POPIA | Protection of Personal Information Act, No. 4 of 2013
SOC 2 | AICPA Trust Services Criteria — Security + Availability
POPIA / SOC 2 | Finding relevant to both frameworks
── YEAR 1 SUMMARY ──
Risks closed | 8 of 21 original risks fully remediated
Risks in progress | 10 of 21 original risks partially remediated
Risks open | 3 of 21 original risks unresolved (R-011 highest priority)
New risks identified | 3 new risks (R-022, R-023, R-024)
Total risks at Month 12 | 24 (21 original + 3 new)